## Example
Gantt Chart - Auto-Generated
| Three Steps: | [5 empty] | Project number: | Project title: | Project leader:
| 1- Project dates. 2- Activities details. 3- Min & Max codes. | [7 empty] | Project start date: | 2019-02-02 | 43498 | Min code
| Gray cells will be calculated for you (fill white cells only). |  |  |  |  | When? (auto-generated) |  |  | Exp. end date: | 2019-07-16 | 43662 | Max code
In days
| ID | Activity (What?) | Start date | Duration | End date |  |  |  | % Complete | Who?
|  | Project start date: | 2019-02-02
1 |  | Activity 1 | 2019-02-02 | 6 | 2019-02-08
2 |  | Activity 2 | 2019-02-05 | 14 | 2019-02-19
3 |  | Activity 3 | 2019-02-12 | 14 | 2019-02-26
4 |  | Activity 4 | 2019-02-12 | 33 | 2019-03-17
5 |  | Activity 5 | 2019-03-03 | 15 | 2019-03-18
6 |  | Activity 6 | 2019-03-13 | 25 | 2019-04-07
7 |  | Activity 7 | 2019-04-07 | 11 | 2019-04-18
8 |  | Activity 8 | 2019-04-07 | 23 | 2019-04-30
9 |  | Activity 9 | 2019-04-21 | 33 | 2019-05-24
10 |  | Activity 10 | 2019-05-14 | 22 | 2019-06-05
11 |  | Activity 11 | 2019-05-17 | 12 | 2019-05-29
12 |  | Activity 12 | 2019-05-17 | 42 | 2019-06-28
13 |  | Activity 13 | 2019-06-02 | 11 | 2019-06-13
14 |  | Activity 14 | 2019-06-05 | 22 | 2019-06-27
15 |  | Activity 15 | 2019-06-12 | 34 | 2019-07-16
16 |  | Activity 16 | 2019-06-12 | 23 | 2019-07-05
17 |  | Activity 17 | 2019-06-23 | 23 | 2019-07-16
18 |  | Activity 18 | 2019-06-23 | 23 | 2019-07-16
|  | Exp. end date: |  |  | 2019-07-16
Continuous Improvement Toolkit . www.citoolkit.com
Guide:
1- Start by setting the start and the expected end date for the entire project.
2- List down all the activities to be performed, their start date, and their expected duration.
3- Enter Min and Max values manually to the Axis Option (use the Min/Max codes highlighted in blue). Click on the chart >> Layout >> Axes >> Primary Horizontal Axis >> More Primary Horizontal Axis Option
Formulas:
End date = IF(OR([Start date]="",[Duration]=""),"",[Start date]+[Duration])