## PDCA Register
| PDCA Register | [6 empty] | ACT | PLAN |  |  | Total | Critical | High | Moderate | Low | Negligible
| Project: | Reduce time spent waiting for lab results | Leader: |  | Cycle #: | 1 |  | 0% | 100% |  | Risk | 0 | 0 | 0 | 0 | 0 | 0
| Process: | Covid-19 molecular testing | Prepared by: |  | Updated: |  |  | 0% | 81.67% |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
|  | You need only to fill the white cells | [5 empty] | CHECK | DO |  | Issue | 0 | 0 | 0 | 0 | 0 | 0
| Select … | What? | Who? | When? | Expected in hours | % | Open/Closed |  |  |  |  | 0 |  |  |  |  | 0
[5 empty] | 153 | 40.31%
| PDCA phase | Activity | Owner | Due date | Activity time | Completion % | Status | Lessons learned
1 | PLAN | Explore all available information | Team |  | 4 | 100% | Closed |  |  | PLAN
2 | PLAN | Brainstorm and generate solution ideas | Team |  | 8 | 100% | Closed |  |  | DO
3 | PLAN | Select the most promising solution | Team |  | 4 | 100% | Closed |  |  | CHECK
4 | PLAN | Develop an action plan to implement the selected solution | Sami |  | 4 | 100% | Closed |  |  | ACT
5 | Do | Perform the steps defined in the action plan | Chadi |  | 32 | 100% | Closed
6 | Do | Collect data on the time spent waiting for results | Chadi |  | 6 | 100% | Closed |  |  | Open
7 | Do | Collect feedback from sample customers | Peter |  | 12 | 45% | Open |  |  | Closed
8 | CHECK | Analyze data and customer feedback | Sara |  | 8 | 0% | Open
9 | CHECK | Assess whether the solution solves the problem | Team |  | 4 | 0% | Open
| CHECK | Share results with key stakeholders | Sami |  | 2 | 0% | Open
10 | CHECK | Discuss further improvements and quick wins | Team |  | 4 | 0% | Open
11 | ACT | Develop an implementation plan | Sami |  | 6 | 0% | Open
12 | ACT | Implement the solution in full-scale | Chadi |  | 40 | 0% | Open
13 | ACT | Document and measure the results obtained | Sami |  | 4 | 0% | Open
14 | ACT | Develop standard operating procedures | Zakaria |  | 3 | 0% | Open
15 | ACT | Train employees on the new process | Sara |  | 12 | 0% | Open
16
17
18
19
20
21
22
23
24
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This PDCA template provides a simple way to plan and monitor your projects and work activities using the PDCA model.
Use this template at the beginning of the project. Start by recording the project title and the other attributes at the top.
Record the Plan Do Check Act activities, owners and due dates.
As the project progresses, regularly review and update completion rates and other information including the lessons learned from each activity.
Remember, just as a circle has no end, the PDCA cycle should be repeated again and again to achieve continuous improvement.