## Example 1
| RACI Matrix | [5 empty] | 8 | 3 | 6 | 13
|  | Process/Project: | Acquiring New Equipment Process |  |  |  | R | A | C | I | R / A | C / I | S
|  | Leader: |  |  |  |  | Responsible | Accountable | Consulted | Informed | Responsible & Accountable | Consulted & Informed | Support
Role / Person
|  |  | Business unit | IT | Finance | Purchasing | Purchasing committee
1 | ID # | Activity / Deliverable
2 |  | Define needs | R | C | I |  | A
3 |  | Technical review | I | R |  |  | C
4 |  | Complete paperwork | R | I | C | C | A
5 |  | Acquire equipment | I | I | I | R | A
6 |  | Follow-up with the supplier | I | C |  | R | I
7 |  | Issue payment |  |  | R | I | I
8 |  | Configure and install | I | R |  |  | I
9 |  | Receive and use | R | C |  |  | I
10
11
12
13
14
Continuous Improvement Toolkit . www.citoolkit.com
Guide:
1st, enter in the left column the project/process activities.
2nd, enter in the blue cells the roles, groups or persons to participate in the project or process.
3rd, for each activity, identify the Responsible, Accountable, Consulted and Informed stakeholders (place the appropriate character (R,A,C, or I)).
Note: you need only to fill the white and blue cells.

## Example 2
| RACI Matrix | [5 empty] | 13 | 11 | 18 | 13
|  | Process/Project: | Assigning Six Sigma Projects |  |  |  | R | A | C | I | R / A | C / I | S
|  | Leader: |  |  |  |  | Responsible | Accountable | Consulted | Informed | Responsible & Accountable | Consulted & Informed | Support
Role / Person
|  |  | Adam (Sponsor) | Fady (Sponsor) | Peter (Master BB) | Sara (Master BB) | Zakaria (Black Belt) | Nermin (Black Belt) | Harvey (Black Belt) | Yusuf (Green Belt)
1 | ID # | Activity / Deliverable
2 | 3114 | Customer complaint reduction | A |  | C | I | C |  | R
3 | 3175 | Changeover time reduction (Line 1) | A | I | C | C |  |  | I | R
4 | 3130 | Changeover time reduction (Line 3) |  | A | C |  |  | R
5 | 3034 | Chemical usage reduction | A | C | I |  | R | C |  | I
6 | 3099 | Machine setup time reduction (Line 1) | A |  |  | C |  |  | R | R
7 | 3157 | Spoilage reduction (Line 2) | I | A | C | C | R | I |  | R
8 | 3103 | Spoilage reduction (Line 4) |  | A |  | C |  | R |  | I
9 | 3219 | Machine tooling consumption (Line 3) | C | A | I |  | R |  | C
10 | 3015 | Machine repair cost reduction (Line 1) | A | I | C | C |  |  | R
11 | 3123 | Electricity consumption reduction | A |  | C |  | I | I |  | R
12 | 3208 | Lacquer usage reduction |  | A | C | I | C | R
13
14
Continuous Improvement Toolkit . www.citoolkit.com
Guide:
1st, enter in the left column the project/process activities.
2nd, enter in the blue cells the roles, groups or persons to participate in the project or process.
3rd, for each activity, identify the Responsible, Accountable, Consulted and Informed stakeholders (place the appropriate character (R,A,C, or I)).
Note: you need only to fill the white and blue cells.