## Log
| Responsibility LOG |  | Jamal | Sali |  |  | Critical | High | Moderate | Low | Negligible
| Project or routine work assignment: | Improving line #4 | Adam | All |  | Jamal | 0 | 2 | 1 | 0 | 0
| Select … |  | Select … | Open/Closed |  | Sali | 0 | 1 | 1 | 0 | 0
[6 empty] | Adam | 0 | 0 | 4 | 1 | 0
| Responsible | Description | Priority | Status |  | All | 0 | 1 | 0 | 0 | 0
1 | All | Define the problem | Moderate | Closed | Jamal
2 | All | Set the objectives | High | Closed | Sali
3 | Sali | Take "before" photos | Moderate | Closed | Adam
4 | All | Design the "As Is" map | High | Closed | All
5 | All | Design the "To Be" map | High | Open
6 | Jamal | Set up and procurement processes | Moderate | Open | Critical
7 | Adam | Remove the existing boards | Moderate | Closed | High
8 | Adam | Paint the area | Moderate | Open | Moderate
9 | Adam | Fix the new boards | Moderate | Open | Low
10 | Adam | Fix the current good boards | Moderate | Open | Negligible
11 | Adam | Prepare and fix the labels | Moderate | Open
12 | Adam | Prepare and fix the spotlights | Low | Open | Open
13 | Sali | Start the posting process | High | Open | Closed
14 | Sali | Take "after" photos | Moderate | Open
15 | Jamal | Estimate benefits gained | High | Open
16 | Jamal | Report benefits and outcomes | High | Open
17
18
19
20
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This template allows teams to track their duties and responsibilities for a project or routine work assignment.
You need only to fill the white cells.

## Dashboard
Responsibility Dashboard
Improving line #4
| Jamal |  | Sali |  | Adam |  | All
| 0 | Critical | 0 | Critical | 0 | Critical | 0 | Critical | 0
| 2 | High | 1 | High | 0 | High | 1 | High | 4
| 1 | Moderate | 1 | Moderate | 4 | Moderate | 0 | Moderate | 6
| 0 | Low | 0 | Low | 1 | Low | 0 | Low | 1
| 0 | Negligible | 0 | Negligible | 0 | Negligible | 0 | Negligible | 0
| 3 |  | 2 |  | 5 |  | 1 |  | 11
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This dashboard allows the team to review the status of their duties at a glance.