## Example
Failure Mode and Effect Analysis (FMEA)
| Document #: |  | Issue date: |  |  |  | Revision #: |  |  | Revision date:
| Process: |  |  | Process owner: |  |  | Project ID: |  |  |  | Project title:
| Identify process steps | How can the process go wrong? | What is the impact if it goes wrong | How severe? | What could cause the failure to occur? | OCC of causes | What controls exist to prevent or detect? | Rate of detect | SEVxOCCxDET | What are the actions for reducing the occurrence of the causes or for improving the detection |  |  | What were the actions implemented
| Process Step (Or product part) | Potential Failure Mode | Potential Failure Effect | SEV | Potential Causes | OCC | Current Controls (prevention/detection) | DET | RPN | Recommended Corrective Action |  |  | Corrective Action
[10 empty] | What? | Who? | When? | Action Taken | SEV | OCC | DET | RPN
1 | Take order | Missing of some required information | Incorrect order | 3 | Lack of attention (taking orders) | 4 | Using of an order-taking checklist | 2 | 24 | Provide stronger validation (order taking system)
2
3 | Prepare order | Wrong amount of ingredients | Defective product | 4 | Broken of equipment or measurement instr. | 1 | Periodic inspection of equipment or instr. | 3 | 12 | -
4 | " | " | " | 4 | Lack of attention (mixing of ingredients) | 3 | Inspection of product before delivery | 4 | 48 | Buy hi-tech inspection device
5
6 | Deliver order | Wrong customer address | Missed delivery | 4 | Lack of attention (taking orders) | 3 | Using of a customer tracking system | 1 | 12 | -
7 | " | Takes too long to deliver products | Delayed delivery | 3 | Traffic jam or too many orders | 3 | Using of GIS technology | 3 | 27 | Hire more people to delivery and buy more delivery cars
8
9
10
11
12
Continuous Improvement Toolkit . www.citoolkit.com
Guide:
The left hand side should be completed during the first draft of the FMEA, and the right hand side are used to track subsequent actions and document reduced RPNs.
Severity rating (high rating is the most severe): (1) Minor failure which is not noticed by the customer. (2) Failure that could be noticed by the customer without negatively affecting customer satisfaction.
(3) Moderate failure that may result in some customer dissatisfaction. (4) Major failure that may generate high level of customer dissatisfaction. (5) Safety issue, adverse impact on end-user, etc.
Occurrence rating (high rating is almost inevitable): (1) The cause of the failure is unlikely to occur. (2) The cause of the failure occurs sometimes.
(3) An occasional occurrence of the cause of the failure. (4) A frequent occurrence of the cause of the failure. (5) The occurrence of the cause of failure is very probable.
Detection rating (high rating means very low chance of failure detection by the current control): (1) Reliable detection control to detect failure mode. (2) High likelihood that the current control will detect failure mode.
(3) Moderate likelihood that the current control will detect failure mode. (4) Low likelihood that the current control will detect failure mode. (5) No control available to detect failure mode or ineffective control.