## Log
| RAID Log | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[9 empty] | Risk | 2 | 1 | 1 | 0 | 0 | 0
| Project title: |  | Project number: |  | Project leader: |  |  |  | Assumption | 2 | 0 | 1 | 1 | 0 | 0
[9 empty] | Issue | 3 | 0 | 0 | 1 | 1 | 1
|  | You need only to fill the white cells. | Revision date: |  | Revision number: |  |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 7 |  |  |  |  | 7
| RAID Category | Description | Impact | Owner | Priority | RPN (for risks) | Status
1 | Issue | Vendor master data is outdated |  |  | Low |  | Open | Risk
2 | Issue | Absence of procurement procedures |  |  | Negligible |  | Open | Assumption
3 | Assumption | Complete information is available prior the approval process |  |  | Moderate |  | Open | Issue
4 | Risk | Long supply delivery time | Impact on the project schedule |  | Critical | 50 | Open | Dependency
5 | Assumption | Proper material and service quality inspection |  |  | High |  | Open
6 | Issue | Absence of prevention maintenance plan |  |  | Moderate |  | Open | Open
7 | Risk | Inability to do required maintenance on time | Impact on the project schedule & cost |  | High | 25 | Open | Closed
8
9 | [7 empty] | Critical
10 | [7 empty] | High
11 | [7 empty] | Moderate
12 | [7 empty] | Low
13 | [7 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This template allows project managers to track risks, assumptions, issues and dependencies.
It should drive to take the necessary actions in order to ensure successful implementation of the project.
Use this log at the beginning of the project, then regularly review and update it as necessary through regular project meetings.

## Dashboard
RAID Dashboard
| Project title: |  |  |  | Project number: |  | Revision date:
| Risks |  | Assumptions |  | Issues |  | Dependencies
| 1 | Critical | 0 | Critical | 0 | Critical | 0 | Critical | 1
| 1 | High | 1 | High | 0 | High | 0 | High | 2
| 0 | Moderate | 1 | Moderate | 1 | Moderate | 0 | Moderate | 2
| 0 | Low | 0 | Low | 1 | Low | 0 | Low | 1
| 0 | Negligible | 0 | Negligible | 1 | Negligible | 0 | Negligible | 1
| 2 |  | 2 |  | 3 |  | 0 |  | 7
Continuous Improvement Toolkit . www.citoolkit.com
Guidelines:
This dashboard allows project teams to review all relevant information related to a project at a glance.