## Portrait
KAIZEN EVENT CHARTER
| EVENT ID: |  | DATE CREATED: |  | REVISION NO.: |  | EVENT PRIORITY (H/M/L):
Visual Management Optimization in the 2-Piece Can Shop Floor
| Kaizen Leader |  | Sponsor |  | Process Owner |  | Facility | CAC
| EVENT TYPE | TRUE | 5S | FALSE | Waste Reduction | FALSE | Root Cause Problem Solving
|  | FALSE | Cycle Time | FALSE | Standard Work | FALSE | Value Stream Mapping
|  | FALSE | Flow Improvement | FALSE | Pull / Kanban | FALSE | Gemba Walk Improvement
|  | FALSE | Line Balancing | FALSE | Production Leveling | FALSE | Quick Changeover
|  | FALSE | Quality | FALSE | Ergonomics | FALSE | Environment, Health and Safety
|  | FALSE | Mistake-Proofing | TRUE | Visual Control | FALSE | Other
| BACKGROUND AND PROBLEM STATEMENT (Reason for Kaizen Event) |  |  |  | VOICE OF THE CUSTOMER (VOC)
| The current shop floor lacks an effective visual management system. Safety visuals, signage, floor markings, and work instructions are inconsistent, faded, or missing. This leads to increased safety risks, inefficient navigation and material flow, and operator confusion and variability in task execution. |  |  |  | Operators: Need clear, standardized instructions and safer working environment. Supervisors: Need better visibility of workflows and status. Auditors: Expect professional, compliant, and intuitive shop floor visuals
| GOAL STATEMENT |  |  |  | METRICS
| Implement a standardized, compliant, and highly visible visual management system across the 2-piece can production floor to improve safety, efficiency, and usability within 5 days. |  |  |  | Metric | Unit | Current | Target
[5 empty] | Visual compliance | % | 65% | ≥ 95% | 1
[5 empty] | Time to locate key areas | Minutes | 4 min | ≤ 1 min | 2
3
| BENEFIT TYPE | TRUE | Quality | TRUE | Cost | FALSE | Delivery
|  | FALSE | Visibility | FALSE | Flexibility | TRUE | Safety
|  | FALSE | Environment | FALSE | Moral | FALSE | Other | Compliance
| TEAM MEMBERS |  |  |  | ON-CALL SUPPORT
| Name | Department | Contact Information | Role | Name | Department | Contact Information | Role
| Kamal | CI | 72710043 | Kaizen Leader | George | Procurement | 70790656 | Support
| Yasmin | Quality | 73700101 | EHS Representative | Aaron | HR | 74789042 | Support
| Adam | Production | 71719188 | Operator | Fatima | Facilities | 79746210 | Support
| Sameer | Engineering | 74742233 | Technician
| SCOPE DEFINITION |  |  |  | EVENT SCHEDULE
| Area / Line | 2-Piece Can Line |  |  | Duration in Days | 5 Days
| Process Name | Can Manufacturing Line |  |  | Start Date | 2026-04-26
| Process Mapped? | Yes |  |  | End Date | 2026-04-30
| Start Point | Raw cup input area |  |  | Hours Each Day | 3 hours
| End Point | Finished can palletizing area |  |  | Daily Start Time | 8:00
| Boundaries | Includes all production floor walkways, machines, utility lines, and operator stations |  |  | Report Date | Day 5 (Final Presentation)
| Out of Scope | Office spaces and W/H areas |  |  | Meetings Location | Shop floor meeting room
| RESOURCES NEEDED (Human, Materials, Equipment, Financial, Training, etc.) |  |  |  | POSSIBLE OBSTACLES (Budget Constraints, Unavailable Resources, etc.)
1 | Floor marking tapes, pipe marking labels, safety signage boards, directional signs |  |  |  | Resistance to change from operators |  |  |  | 1
2 | Label printers and laminators |  |  |  | Production downtime constraints |  |  |  | 2
3 | Budget for signage and materials ~$2,000 | [7 empty] | 3
4 | Training (Visual management standards and 5S principles) | [7 empty] | 4
| KEY DELIVERABLES (In order of importance) |  |  |  | DAILY MILESTONES
1 | Fully implemented floor marking system (walkways, hazards, storage zones) |  |  |  | DAY 1: Kickoff - Gemba walk - Current state assessment
2 | Clear directional and wayfinding signage across the shop floor |  |  |  | DAY 2: Design signage and layouts - Develop visual standards
3 | Standardized pipe marking (flow direction, contents, hazards) |  |  |  | DAY 3: Begin implementation (floor marking, signage installation)
4 | Updated and compliant safety visuals and warning signage |  |  |  | DAY 4: Complete implementation (Install work instructions and posters)
5 | Standardized visual management guideline for the facility |  |  |  | DAY 5: Audit and adjust - Standardize and document - Final presentation
|  |  | Name |  | Signature |  | Date
Kaizen Leader:
Sponsor:
Process Owner:
Signatures (The signatures of the people above document approval of the Kaizen Event Charter) The Kaizen Leader is empowered by this Kaizen Event Charter to proceed with the event as outlined above
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This worksheet is designed to capture the essential elements of a Kaizen event, such as the problem statement, goals, metrics, team structure, and implementation plan, in a clear and organized format. It enables alignment among stakeholders, ensures a common understanding of objectives, and provides a structured roadmap for successful execution. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | Enter a concise and descriptive title that reflects the focus area and process scope.
2 | Select the appropriate Event Type based on the objective of the Kaizen event (e.g., 5S, waster reduction, etc.) |  | LEARN MORE
3 | In the Problem Statement section, clearly describe the current condition, key issues, and their impact. |  | Version Number: 3.1
4 | Capture the VoC by identifying internal or external stakeholders and summarizing their needs or concerns.
5 | Define a measurable Goal Statement that specifies the expected improvement. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | In the Metrics section, list relevant KPIs with their units, current values, and target values to track success. |  | info@citoolkit.com
7 | List all Team Members involved in the event, including their roles, functional areas and contact information.
8 | Fill the rest of the remaining sections including scope, resources, key deliverables and daily milestones. |  | To learn more about other continuous improvement tools, visit the Citoolkit website at:
9 | Secure signatures from key stakeholders to confirm alignment and approval of the event plan. |  | www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com