## Kanban Board
| KANBAN BOARD |  | A | HIGH PRIORITY | U | URGENT | W | WAITING OR PENDING
|  |  | BOARD TITLE | Lean Six Sigma Deployment Board |  |  | WEEK
|  | BACKLOG |  | TO DO |  | DOING |  | DONE
1 |  | Establish performance tracking and reporting Owner: CI PMO Due: 10 Aug |  | Conduct DMAIC training (Green Belt) Owner: LSS Expert Due: 25 Jul |  | Identify priority processes Owner: CI PMO Due: 21 May |  | Finalize deployment charter Owner: Engagement Manager Due to: 05 Apr
2 |  | Standardize successful practices Owner: Process CI PMO Due: 24 Aug |  | Select pilot areas Owner: Executive Sponsor Due: 08 Jul |  | Facilitate VOC workshops Owner: LSS Expert Due: 01 Jun |  | Set up governance and steering committee Owner: Executive Sponsor Due to: 23 Apr
3 |  | Review pilot results and lessons learned Owner: Engagement Manager Due: 14 Aug | A | Build LSS project pipeline Owner: CI PMO Due: 20 Jul |  | Conduct baseline LSS maturity assessment Owner: LSS Expert Due: 14 May |  | Develop LSS deployment roadmap Owner: LSS Expert Due to: 09 Apr
4 |  | Launch pilot projects (selected processes) Owner: LSS Expert Due: 06 Aug |  | Draft LSS training plan Owner: LSS Expert Due: 11 Jun |  | Prepare communication campaign Owner: Engagement Manager Due to: 29 Apr
5 |  | Define pilot project charters Owner: LSS Expert Due: 30 Jul |  |  | W | Approve governance structure Owner: Executive Sponsor Due to: 29 Apr
6
7
8
9
10
11
12
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Data (hidden)
PRIORITY | STATUS
Critical | Not Started
High | Delayed
Moderate | On Track
Low | Done

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This Kanban Board Template provides a simple and efficient way to manage activities in a wide range of environments. It helps teams to instantly see what is pending, what is in progress, and what has been completed. The board is fully customizable and you to increase or reduce the number of columns to fit your team’s needs. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | Start by entering the board title and the current week of the year at the top of the board.
2 | Label the four columns as per your needs, for example: Backlog, To Do, Doing, Done. |  | LEARN MORE
3 | For each activity card, clearly write the activity name, assign the responsible owner, and specify the due date. |  | Version Number: 3.1
4 | Place each card in the column that reflects its current status.
5 | Move cards forward as work progresses. For example, from Backlog → To Do → Doing → Done. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | Review the cards regularly to ensure owners are progressing and due dates remain accurate. |  | info@citoolkit.com
7 | Highlight or flag any card that is waiting, blocked or delayed for immediate attention.
To learn more about other continuous improvement tools, visit the Citoolkit website at:
www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com