## Risk Register
PROJECT RISK REGISTER
[14 empty] | Impact | 1- Minor | 2- Low | 3- Moderate | 4- High | 5- Very high
| PROJECT TITLE |  |  |  | ASSESSOR |  | ASSESSMENT DATE | [6 empty] | Likelihood | 1- Very unlikely | 2- Unlikely | 3- Likely | 4- Very likely | 5- Certain
[14 empty] | Risk Rate | Negligible | Low | Medium | High | Critical
| 1. RISK IDENTIFICATION | [5 empty] | 2. RISK ANALYSIS | [6 empty] | 3. RISK RESPONSE / TREATMENT
|  | Unique identifier | When the risk was identified? | Detailed explanation of the risk | The consequence if the risk occurs | Identifies the origin of the risk | Current control measures in place to mitigate the risk | Potential impact if the risk occurs | The probability that the risk will occur | RPN (P*I) | Actions to reduce or eliminate the risk | Risk owner | Timeline for starting the mitigation action or response plan | The actions that have been taken to reduce or eliminate the risk | New impact rating | New likelihood rating | RPN (P*I) | Open, Closed, Under Review | When the risk is no longer considered a threat
|  | Risk ID | Date Raised | Risk Description | Risk Effect | Risk Cause / Source | Existing Controls | INITIAL RISK RATING |  |  | RECOMMENDED CORRECTIVE / METIGATION ACTION |  |  | Response Taken | RESIDUAL RISK RATING |  |  | Risk Status | Date Closed
[8 empty] | Impact | Likelihood | Risk Rate | What? | Who? | When? |  | Impact | Likelihood | Risk Rate
1
2 | [19 empty] | Risk Matrix |  | Impact
3 | [21 empty] | 1- Minor | 2- Low | 3- Moderate | 4- High | 5- Very high
4 | [19 empty] | Likelihood | 5- Certain | Medium | High | High | Critical | Critical
5 | [20 empty] | 4- Very likely | Low | Medium | High | High | Critical
6 | [20 empty] | 3- Likely | Low | Medium | Medium | High | Critical
7 | [20 empty] | 2- Unlikely | Low | Low | Medium | Medium | High
8 | [20 empty] | 1- Very unlikely | Negligible | Low | Low | Medium | High
9
10
11
12
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This risk register template helps identify, analyze, and manage risks for any project. It offers a clear approach to identifying risks, assessing their probability and impact, and prioritizing them based on their risk score. Teams can then plan mitigation and corrective actions to manage risks effectively. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | This Risk Register teamplate is divided into three sections: Risk Identification, Risk Analysis, and Risk Response.
2 | The risk identification section captures essential information about each risk, such as the risk title and category. |  | LEARN MORE
3 | In the risk analysis section, risks should be analyzed for their potential impact and likelihood. |  | Version Number: 3.1
4 | In the risk response section, plans should be set to respond to risks and responsibilities should be assigned.
5 | A risk matrix located on the far right helps provide a clear visual representation of risk levels. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | Ensure closed risks are promptly removed from the register once they are finalized. |  | info@citoolkit.com
7 | It is recommended to protect the Risk Register worksheet before using it in an actual project.
8 | Ensure you fill in only the white cells as the other cells are either auto-populated or locked for editing. |  | To learn more about other continuous improvement tools, visit the Citoolkit web site at:
www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com