## Slide 1
RISK ID | RISK DESCRIPTION | CATEGORY Financial, etc. | PROPOSED ACTIONS To reduce or eliminate the risk | DEADLINE | RESPONSIBLE | IMPACT (1-4) | LIKELIHOOD (1-4)
F1 | Lack of Financial Representation | Financial | Assign a dedicated financial representative | 23/09 | Sponsor | 4 | 3
L1 | Part-Time Technical Leadership | Leadership | Appoint a deputy leader to fill the gap | Immediately | Project Leader | 3 | 2
G1 | Limited Availability of Team Resources | Governance | Ensure commitments are respected | 15/09 | HR Manager | 3 | 4
L2 | Absence of a Six Sigma Champion | Leadership | Appoint a champion immediately | Immediately | Sponsor | 4 | 3
G2 | Undefined Process Ownership | Governance | Establish process owners and roles | Immediately | Sponsor | 2 | 2
L3 | Lack of Management Support | Leadership | Set regular sessions with senior management | Immediately | Sponsor | 4 | 1
Low (1)
High (4)
IMPACT
High (4)
Low (1)
LIKELIHOOD
1 | 2 | 3 | 4
MINOR | MODERATE | HIGH | VERY HIGH
IMPACT
1 | 2 | 3 | 4
UNLIKELY | LIKELY | VERY LIKELY | CERTAIN
LIKELIHOOD
RISK RATING
Low: Keep in mind
Medium: Action required
High: Urgent measures required
F1
L1
G1
L2
G2
L3
Notes: Project Risk Register Template – Table Theme – © Copyright Continuous Improvement Toolkit . www.citoolkit.com

## Slide 2
Low (1)
High (4)
IMPACT
High (4)
Low (1)
LIKELIHOOD
1 | 2 | 3 | 4
MINOR | MODERATE | HIGH | VERY HIGH
IMPACT
1 | 2 | 3 | 4
UNLIKELY | LIKELY | VERY LIKELY | CERTAIN
LIKELIHOOD
RISK RATING
Low: Keep in mind
Medium: Action required
High: Urgent measures required
F1
L1
G1
L2
G2
L3
RISK DESCRIPTION
PROPOSED ACTION
RISK ID
CATEGORY
RESPONSIBLE
IMPACT
LIKELIHOOD
DEADLINE
The technical leader not being full-time, which could result in insufficient guidance
There is a risk that yellow belts may not be fully available to contribute to the project
The absence of a financial representative assigned to the project may lead to mismanagement of funds
The lack of a designated Six Sigma Champion poses a risk of insufficient support and lack of direction
Not having a defined process owner could result in unclear accountability and hinder decision-making
A risk of insufficient visible management support, which may lead to reduced stakeholder engagement
Appoint a deputy leader to fill the gap
Ensure commitments are respected
Assign a dedicated financial representative
Appoint a champion immediately
Establish process owners and roles
Set regular meetings with senior management
L1
G1
F1
L2
G2
L3
Leadership
Governance
Financial
Leadership
Governance
Leadership
Project Leader
HR Manager
Sponsor
Sponsor
Sponsor
Sponsor
3
3
4
4
2
4
2
4
3
3
2
1
Immediately
15/09
23/09
Immediately
Immediately
Immediately
Notes: Project Risk Register Template – Block Theme– © Copyright Continuous Improvement Toolkit . www.citoolkit.com