## Risk Register
PROJECT RISK REGISTER
[14 empty] | Impact | 1- Minor | 2- Low | 3- Moderate | 4- High | 5- Very high
| PROJECT TITLE |  |  |  | ASSESSOR |  | ASSESSMENT DATE | [6 empty] | Likelihood | 1- Very unlikely | 2- Unlikely | 3- Likely | 4- Very likely | 5- Certain
[14 empty] | Risk Rate | Negligible | Low | Medium | High | Critical
| 1. RISK IDENTIFICATION | [5 empty] | 2. RISK ANALYSIS | [6 empty] | 3. RISK RESPONSE / TREATMENT
|  | Unique identifier | When the risk was identified? | Detailed explanation of the risk | The consequence if the risk occurs | Identifies the origin of the risk | Current control measures in place to mitigate the risk | Potential impact if the risk occurs | The probability that the risk will occur | RPN (P*I) | Actions to reduce or eliminate the risk | Risk owner | Timeline for starting the mitigation action or response plan | The actions that have been taken to reduce or eliminate the risk | New impact rating | New likelihood rating | RPN (P*I) | Open, Closed, Under Review | When the risk is no longer considered a threat
|  | Risk ID | Date Raised | Risk Description | Risk Effect | Risk Cause / Source | Existing Controls | INITIAL RISK RATING |  |  | RECOMMENDED CORRECTIVE / METIGATION ACTION |  |  | Response Taken | RESIDUAL RISK RATING |  |  | Risk Status | Date Closed
[8 empty] | Impact | Likelihood | Risk Rate | What? | Who? | When? |  | Impact | Likelihood | Risk Rate
1 | Negligible | R272 | 2024-09-15 | The absence of a financial representative assigned to the project may lead to mismanagement of funds and budgetary constraints. | Mismanagement of funds, budget overruns, and potential delays due to financial constraints. | Lack of a financial expert on the project team. | Project management oversight on budget issues. | 4- High | 3- Likely | High | Assign a dedicated financial representative and ensure financial reporting at key milestones. | Project Sponsor | 2024-09-23 | Assign a dedicated financial representative and ensure financial reporting at key milestones. | 1- Minor | 1- Very unlikely | Negligible | Closed | 2024-09-27
2 | Low | R177 | 2024-11-03 | The project risks being adversely affected by the technical leader not being full-time, which could result in insufficient guidance and oversight. | Delayed project progress or technical misalignment. | Technical leader split between multiple projects. | Frequent check-ins with the technical leader. | 3- Moderate | 3- Likely | Medium | Appoint a deputy leader to fill the gap. | Project Manager | Immediately | Appoint a deputy leader to fill the gap. | 2- Low | 2- Unlikely | Low | Under Review |  | Risk Matrix |  | Impact
3 | Low | R473 | 2024-08-09 | There is a risk that yellow belts and other team members may not be fully available to contribute to the project, potentially delaying progress and impacting deliverables. | Project delays, incomplete deliverables, and reduced quality. | Competing priorities for team members. | Resource planning and scheduling. | 3- Moderate | 4- Very likely | High | Ensure that resources are dedicated and their time commitments are respected. | HR Manager | 2024-09-02 | Ensure that resources are dedicated. | 3- Moderate | 1- Very unlikely | Low | Open |  |  |  | 1- Minor | 2- Low | 3- Moderate | 4- High | 5- Very high
4 | Negligible | R312 | 2024-09-24 | The lack of a designated Six Sigma Champion poses a risk of insufficient support leading to a lack of direction and momentum. | Lack of leadership could affect the project negatively. | No designated Six Sigma Champion. | General project oversight by the steering committee. | 5- Very high | 3- Likely | Critical | Appoint a Six Sigma Champion immediately. | Project Sponsor | Immediately | Appoint a Six Sigma Champion immediately. | 1- Minor | 1- Very unlikely | Negligible | Closed | 2024-09-30 | Likelihood | 5- Certain | Medium | High | High | Critical | Critical
5 | Medium | R516 | 2024-10-02 | Not having a defined process owner, which could result in unclear accountability and hinder decision-making. | Delayed decisions and bottlenecks in process improvements. | Lack of clear roles and responsibilities for processes. | None | 3- Moderate | 3- Likely | Medium | Establish process owners and roles. | Senior Leadership | Immediately | Establish process owners and roles. | [6 empty] | 4- Very likely | Low | Medium | High | High | Critical
6 | Medium | R102 | 2024-07-03 | The project faces a risk of insufficient visible management support, which may lead to low team morale and reduced stakeholder engagement. | Potential project delays, and disengagement from key team members. | Management's focus on other priorities, unclear communication of the project's value to leadership. | Periodic project status reports shared with management. | 4- High | 2- Unlikely | Medium | Schedule regular meetings with senior management to align on goals. | Project Sponsor | Immediately | Schedule regular meetings with senior management to align on goals. | [6 empty] | 3- Likely | Low | Medium | Medium | High | Critical
7 | [20 empty] | 2- Unlikely | Low | Low | Medium | Medium | High
8 | [20 empty] | 1- Very unlikely | Negligible | Low | Low | Medium | High
9
10
11
12
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This risk register template helps identify, analyze, and manage risks for any project. It offers a clear approach to identifying risks, assessing their probability and impact, and prioritizing them based on their risk score. Teams can then plan mitigation and corrective actions to manage risks effectively. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | This Risk Register teamplate is divided into three sections: Risk Identification, Risk Analysis, and Risk Response.
2 | The risk identification section captures essential information about each risk, such as the risk title and category. |  | LEARN MORE
3 | In the risk analysis section, risks should be analyzed for their potential impact and likelihood. |  | Version Number: 3.1
4 | In the risk response section, plans should be set to respond to risks and responsibilities should be assigned.
5 | A risk matrix located on the far right helps provide a clear visual representation of risk levels. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | Ensure closed risks are promptly removed from the register once they are finalized. |  | info@citoolkit.com
7 | It is recommended to protect the Risk Register worksheet before using it in an actual project.
8 | Ensure you fill in only the white cells as the other cells are either auto-populated or locked for editing. |  | To learn more about other continuous improvement tools, visit the Citoolkit web site at:
www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com