## Example 1
| RACI MATRIX | [5 empty] | 8 | 3 | 6 | 13
|  | PROCESS/PROJECT | Acquiring New Equipment Process |  |  |  | R | A | C | I | R / A | C / I | S
|  | ANALYST |  |  |  |  | Responsible | Accountable | Consulted | Informed | Responsible & Accountable | Consulted & Informed | Support
ROLE / PERSON
|  |  | Business unit | IT | Finance | Purchasing | Purchasing committee
1 | ID # | ACTIVITY / DELIVERABLE
2 |  | Define needs | R | C | I |  | A
3 |  | Technical review | I | R |  |  | C
4 |  | Complete paperwork | R | I | C | C | A
5 |  | Acquire equipment | I | I | I | R | A
6 |  | Follow-up with the supplier | I | C |  | R | I
7 |  | Issue payment |  |  | R | I | I
8 |  | Configure and install | I | R |  |  | I
9 |  | Receive and use | R | C |  |  | I
10
11
12
13
14
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Example 2
| RACI MATRIX | [5 empty] | 13 | 11 | 18 | 13
|  | PROCESS/PROJECT | Assigning Six Sigma Projects |  |  |  | R | A | C | I | R / A | C / I | S
|  | ANALYST |  |  |  |  | Responsible | Accountable | Consulted | Informed | Responsible & Accountable | Consulted & Informed | Support
ROLE / PERSON
|  |  | Adam (Sponsor) | Fady (Sponsor) | Peter (Master BB) | Sara (Master BB) | Zakaria (Black Belt) | Nermin (Black Belt) | Harvey (Black Belt) | Yusuf (Green Belt)
1 | ID # | ACTIVITY / DELIVERABLE
2 | 3114 | Customer complaint reduction | A |  | C | I | C |  | R
3 | 3175 | Changeover time reduction (Line 1) | A | I | C | C |  |  | I | R
4 | 3130 | Changeover time reduction (Line 3) |  | A | C |  |  | R
5 | 3034 | Chemical usage reduction | A | C | I |  | R | C |  | I
6 | 3099 | Machine setup time reduction (Line 1) | A |  |  | C |  |  | R | R
7 | 3157 | Spoilage reduction (Line 2) | I | A | C | C | R | I |  | R
8 | 3103 | Spoilage reduction (Line 4) |  | A |  | C |  | R |  | I
9 | 3219 | Machine tooling consumption (Line 3) | C | A | I |  | R |  | C
10 | 3015 | Machine repair cost reduction (Line 1) | A | I | C | C |  |  | R
11 | 3123 | Electricity consumption reduction | A |  | C |  | I | I |  | R
12 | 3208 | Lacquer usage reduction |  | A | C | I | C | R
13
14
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This RACI matrix template provides a simple and straightforward way to identify and map the relationships between stakeholders and project or process activities. Once filled out, the matrix provides a clear view of who is responsible, accountable, consulted, and informed for each activity. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | In the left column, list the activities involved in your project or process.
2 | In the blue header cells, enter the roles, groups, or individuals participating in the project or process. |  | LEARN MORE
3 | For each activity, identify the stakeholders’ roles by placing the appropriate letter in the corresponding cell. |  | Version Number: 3.1
4 | Use the letters R, A, C, and I to indicate each role: Responsible, Accountable, Consulted, and Informed.
5 | You may adjust the participation types as needed to best fit your project or process. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | Note: Only the white and blue cells are intended for user input. |  | info@citoolkit.com
To learn more about other continuous improvement tools, visit the Citoolkit website at:
www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com