## Risk Register
PROJECT RISK REGISTER
PROJECT TITLE |  |  | ASSESSOR |  | ASSESSMENT DATE
RISK MATRIX |  | Impact | [5 empty] | Risk | Impact | Likelihood
|  | 1- Minor | 2- Low | 3- Moderate | 4- High | 5- Very high | A | The lack of a designated Six Sigma Champion could lead to poor direction. | 4- High | 1- Very unlikely
Likelihood | 5- Certain | [5 empty] | B | Not having a defined process owner could lead to unclear accountability. | 3- Moderate | 3- Likely
| 4- Very likely | [5 empty] | C | A part-time technical leader could result in insufficient technical guidance. | 3- Moderate | 2- Unlikely
| 3- Likely | [5 empty] | D | Limited availability of Yellow Belts may result in delaying progress. | 4- High | 2- Unlikely
| 2- Unlikely | [5 empty] | E | The absence of a financial representative may lead to mismanagement of funds. | 2- Low | 1- Very unlikely
| 1- Very unlikely | [5 empty] | F
| Impact | 1- Minor | 2- Low | 3- Moderate | 4- High | 5- Very high
| Likelihood | 1- Very unlikely | 2- Unlikely | 3- Likely | 4- Very likely | 5- Certain
| Risk Rate | Negligible | Low | Medium | High | Critical
#VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com
A
B
C
D
E
F

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This risk analysis heat map template allows to document and assess risks by categorizing them within the matrix based on their impact and likelihood of occurrence. Risk impact is often shown on the vertical axis (Y), while risk likelihood of occurrence is shown on the horizontal axis (X) |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | Write the identified risks under the "Risk" column.
2 | Select the impact and likelihood values for each identified risk item. |  | LEARN MORE
3 | Manually move the character icons to their corresponding positions on the risk matrix. |  | Version Number: 3.1
4 | It is recommended to protect the Risk Register worksheet before using it in an actual project.
5 | Ensure you fill in only the white cells as the other cells are either auto-populated or locked for editing. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
info@citoolkit.com
To learn more about other continuous improvement tools, visit the Citoolkit web site at:
www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com