## Register
WASTE RECORDING AND TRACKING
WASTE TYPES / TIMWOODS
| VALUE STREAM | Food Production | [5 empty] | TRANSPORT | OVERPRODUCTION
| PROCESS / WORK AREA | Filling & Packaging Line | [5 empty] | INVENTORY | OVERPROCESSING
| PREPARED BY | Lean Coordinator | [5 empty] | MOTION | DEFECTS
| PERIOD | Q1 2025 | [5 empty] | WAITING | SKILLS
|  | TIMWOODS CATEGORIES | WHAT IS THE WASTE & WHY IT MATTERS |  | OR SEVERITY | NOT FULL RCA | QUICK COUNTERMEASURE IDEAS |  |  | TRACK PROGRESS
| PROCESS STEP | WASTE TYPE | DESCRIPTION / IMPACT | NVA TIME | PRIORITY | POSSIBLE CAUSE | PROPOSED ACTION / COMMENT | OWNER | DUE DATE | STATUS
1 | Packaging | INVENTORY | Large stock of unused labels occupying space. | - | MEDIUM | Old forecast not updated. | Reduce lot sizes. | Inventory Controller | 12/01 | CLOSED | PLAN
2 | Weighing | MOTION | Operators bend frequently to reach scales. | 5 min/shift | LOW | Poor workstation ergonomics. | Raise scale platform. | Maintenance | 17/01 | CLOSED | DO
3 | Labeling | DEFECTS | Incorrect label applied. | 5 min/rework | HIGH | Wrong label roll selection. | Use label color coding. | QC | 19/01 | IN PROGRESS | CHECK
4 | Packaging | WAITING | Downtime due to label printer resets. | 6 min/event | HIGH | Outdated printer. | Replace printer. | IT | 01/02 | IN PROGRESS
5 | Packaging | TRANSPORT | Operators walk repeatedly to retrieve film rolls. | 12 min/shift | MEDIUM | Film stored far from the line. | Relocate film to point-of-use rack. | Line Leader | 10/02 | IN PROGRESS
6 | Cutting | OVERPRODUCTION | Cutting more portions than needed. | - | HIGH | Batch mentality. | Switch to pull-based cutting. | Production | 23/02 | PENDING
7 | Sealing | DEFECTS | Packages not sealed properly. | 17 min/shift rework | HIGH | Misaligned sealing jaws. | Schedule daily check. | Maintenance | 03/03 | CLOSED
8 | Filling | OVERPRODUCTION | Extra sauces prepared “just in case.” | - | MEDIUM | Inconsistent demand communication. | Implement hourly consumption check. | Team Leader | 08/03 | IN PROGRESS
9 | Packaging | SKILLS | Operators not involved in problem-solving. | - | LOW | No structured improvement meetings. | Introduce daily huddles. | Supervisor | 14/03 | PLANNED
10 | QC | OVERPROCESSING | Double-checking weight after automated weighing. | 4 min/shift | LOW | Lack of trust in automation. | Calibrate equipment and retrain staff. | QC | 14/03 | PLANNED
11
12 | [10 empty] | ACT
13
14 | [10 empty] | OPEN
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Guide
GUIDE
| DESCRIPTION |  | TERMS AND CONDITIONS
| This Waste Recording and Tracking Template offers a structured approach to log and track various types of waste or Muda across a process, value stream, or work area. It uses the TIMWOODS framework to ensure all major waste categories are consistently identified and addressed. It covers waste identification, prioritization, accountability, and follow-up which makes it suitable as a waste register. |  | This template is made for personal and business use only.
It may not be made available publicly without prior written consent of CIToolkit.
Redistribution, reselling, lease, license, sub-license or offering this template to a third party are not allowed.
This includes uploading it to another website & offering it without reference or maintaining CIToolkit information.
| INSTRUCTIONS |  | This template can be customized and modified to fit your requirements. We are not liable however for its misuse.
1 | Begin by entering all header attributes, such as the process to be reviewed and the review period.
2 | Record the specific process step, workstation, or area where the waste was observed. |  | LEARN MORE
3 | Select the waste category that best represents the waste using the TIMWOODS framework. |  | Version Number: 3.1
4 | Describe what you observed and explain how it affects flow, efficiency, quality, or customer value.
5 | Estimate the amount of time spent on the wasted activity to prioritize which wastes should be addressed first. |  | For any help or more information, or to report any errors in the worksheet, please email us at:
6 | Assign a priority score based on factors such as impact, frequency, time, safety, or ease of resolution. |  | info@citoolkit.com
7 | Enter the most likely reasons behind the waste as a preliminary step before a full root cause analysis.
8 | Document the proposed countermeasure, improvement idea, or relevant remarks. |  | To learn more about other continuous improvement tools, visit the Citoolkit website at:
9 | Note: Only the white cells are intended for user input. |  | www.citoolkit.com
| #VALUE! | © Copyright Continuous Improvement Toolkit. www.citoolkit.com

## Data (hidden)
WASTE TYPES (CATEGORIES) |  |  |  | PRIORITY | STATUS | PROCESS
TRANSPORT | 1 | TRANSPORT | T | HIGH | PLANNED | Cutting
INVENTORY | 1 | INVENTORY | I | MEDIUM | IN PROGRESS | Weighing
MOTION | 1 | MOTION | M | LOW | PENDING | Filling
WAITING | 1 | WAITING | W |  | CLOSED | Sealing
OVERPRODUCTION | 2 | OVERPRODUCTION | O |  |  | Labeling
OVERPROCESSING | 1 | OVERPROCESSING | O |  |  | QC
DEFECTS | 2 | DEFECTS | D |  |  | Packaging
SKILLS | 1 | SKILLS | S